## Sheet1
Requirements Traceability Matrix
Project Name: |  | OrangeHRM |  | Document Author: |  | QA Team
Requirement ID / SRS ID | Requirement Name / Description | Requested / Approved By: | Scope Deliverable or Feature | Scope ID | User Story or Work Package | Assigned To | Test Case | Current Staus | Bug ID
Req - 01 / SRS - 3 | Log in to the OrangeHRM System (HR Admin) | Product Owner | Log in | Scope - 3 | As an HR Admin, I want to log in to access administrative functions | Ahmed Abdallatif | TC - 1 to TC - 16 | Failed | Bug - 1 / Bug - 2
Req - 02 / SRS - 3 | Log in to the OrangeHRM System (ESS-User) | Product Owner | Log in | Scope - 3 | As an ESS-User, I want to log in to view/edit my personal information | Ehab Halabi | TC - 17 to TC - 21 | Failed | Bug - 3
Req - 03 / SRS - 3.1.1 | ESS-User views/edits personal details | Product Owner | My Info > Personal Details | Scope - 3.1 | As an ESS-User, I want to update my personal details while restricted fields remain read-only | Ehab Halabi | TC - 22 to TC - 31 | Failed | Bug - 4 / Bug - 5 / Bug - 6 / Bug - 7
Req - 04 / SRS - 3.1.2 | ESS-User uploads profile photo (max 1MB) | Product Owner | My Info > Photograph | Scope - 3.1.1 | As an ESS-User, I want to upload a profile photo adhering to size/format rules | Ehab Halabi | TC - 32 to TC - 38 | Failed | Bug - 8
Req - 05 / SRS - 3.1.3 | ESS-User updates contact details (address, phone, email) | Product Owner | My Info > Contact Details | Scope - 3.1.3 | As an ESS-User, I want to edit my contact details to keep HR records current | Ehab Halabi | TC - 39 to TC - 49 | Failed | Bug - 9 / Bug - 10
Req - 06 / SRS - 3.1.4 | ESS-User manages emergency contacts (add/delete) | Product Owner | My Info > Emergency Contacts | Scope - 3.1.4 | As an ESS-User, I want to manage emergency contacts for HR use | Ehab Halabi | TC - 50 to TC - 53 | Passed | ____
Req - 07 / SRS - 3.1.5 | ESS-User manages dependents (add/delete) | Product Owner | My Info > Dependents | Scope - 3.1.5 | As an ESS-User, I want to list dependents for HR benefits | Hanna Farhoud | TC - 54 to TC - 57 | Passed | ____
Req - 08 / SRS - 3.1.6 | ESS-User manages immigration documents | Product Owner | My Info > Immigration | Scope - 3.1.6 | As an ESS-User, I want to upload immigration docs with expiry dates | Hanna Farhoud | TC - 58 to TC - 60 | Passed | ____
Req - 09 / SRS - 3.1.7 | ESS-User views job details (read only) | Product Owner | My Info > Job | Scope - 3.1.7 | As an ESS-User, I want to view my job title, department, and contract dates | Hanna Farhoud | TC - 61 | Passed | ____
Req - 10 / SRS - 3.1.8 | Salary details hidden from ESS-User | Product Owner | My Info > Salary | Scope - 3.1.8 | As an ESS-User, I expect salary data to be accessible only to HR Admins | Hanna Farhoud | TC - 62 | Passed | ____
Req - 11 / SRS - 3.1.9 | ESS-User views supervisor/subordinate list | Product Owner | My Info > Report To | Scope - 3.1.9 | As an ESS-User, I want to see my reporting hierarchy | Hanna Farhoud | TC - 63 to TC - 64 | Passed | ____
Req - 12 / SRS - 3.1.10 | ESS-User manages qualifications | Product Owner | My Info > Qualifications | Scope - 3.1.10 | As an ESS-User, I want to update my professional qualifications | Majd Abu Hassanien | TC - 65 to TC - 77 | Failed | Bug - 11 / Bug - 12
Req - 13 / SRS - 3.1.11 | ESS-User manages memberships | Product Owner | My Info > Membership | Scope - 3.1.11 | As an ESS-User, I want to list my professional memberships | Majd Abu Hassnain | TC - 78 to TC - 87 | Passed | ____
Req - 14 / SRS - 3.2.1 | Admin creates/edits/deletes users | Product Owner | Admin > User Management > Users | Scope - 3.2.1 | As an HR Admin, I want to manage user accounts with roles and statuses | Ahmed Abdallatif | TC - 88 to TC - 165 | Failed | Bug - 13 / Bug - 14 / Bug - 15 / Bug - 16 / Bug - 17 / Bug - 18 / Bug - 19
Req - 15 / SRS - 3.2.2.1 | Admin defines job titles | Product Owner | Admin > Job > Job Titles | Scope - 3.2.2 | As an HR Admin, I want to create validated job titles | Ahmed Abdallatif | TC - 166 to TC - 209 | Failed | Bug - 20 / Bug - 21 / Bug - 22 / Bug - 23 / Bug - 24 / Bug - 25
Req - 16 / SRS - 3.2.2.2 | Admin defines pay grades | Product Owner | Admin > Job > Pay Grades | Scope - 3.2.2 | As an HR Admin, I want to set logical salary ranges | Ahmed Abdallatif | TC - 210 to TC - 241 | Failed | Bug - 26 / Bug - 27 / Bug - 28 / Bug - 29 / Bug - 30
Req - 17 / SRS - 3.2.2.3 | Admin manages employment statuses | Product Owner | Admin > Job > Employment Status | Scope - 3.2.2 | As an HR Admin, I want to track employee statuses | Majd Abu Hassanien | TC - 242 to TC - 248 | Passed | ____
Req - 18 / SRS - 3.2.2.4 | Admin defines job categories | Product Owner | Admin > Job > Job Categories | Scope - 3.2.2 | As an HR Admin, I want to categorize jobs with naming rules | Ahmed Abdallatif | TC - 249 to TC - 261 | Failed | Bug - 31 / Bug - 32 / Bug - 33
Req - 19 / SRS - 3.2.2.5 | Admin manages work shifts | Product Owner | Admin > Job > Work Shifts | Scope - 3.2.2 | As an HR Admin, I want to assign employees to shifts | Majd Abu Hassanien | TC - 262 to TC - 268 | Passed | ____
Req - 20 / SRS - 3.2.3.1 | Admin edits company info (name, tax ID) | Product Owner | Admin > Organization > General | Scope - 3.2.3 | As an HR Admin, I want to update company details | Hazem Lababidi | TC - 269 to TC - 273 | Failed | Bug - 34
Req - 21 / SRS - 3.2.3.2 | Admin adds/manages locations | Product Owner | Admin > Organization > Locations | Scope - 3.2.3 | As an HR Admin, I want to track office locations | Hazem Lababidi | TC - 274 to TC - 279 | Passed | ____
Req - 22 / SRS - 3.2.3.3 | Admin defines company structure | Product Owner | Admin > Organization > Structure | Scope - 3.2.3 | As an HR Admin, I want to map organizational hierarchy | Hazem Lababidi | TC - 280 to TC - 283 | Passed | ____
Req - 23 / SRS - 3.2.4.1 | Admin defines skills | Product Owner | Admin > Qualifications > Skills | Scope - 3.2.4 | As an HR Admin, I want to standardize employee skills | Hazem Lababidi | TC - 284 to TC - 286 | Passed | ____
Req - 24 / SRS - 3.2.4.2 | Admin manages education levels | Product Owner | Admin > Qualifications > Education | Scope - 3.2.4 | As an HR Admin, I want to list accepted education levels | Hazem Lababidi | TC - 287 to TC - 288 | Passed | ____
Req - 25 / SRS - 3.2.4.3 | Admin manages licenses | Product Owner | Admin > Qualifications > Licenses | Scope - 3.2.4 | As an HR Admin, I want to track employee certifications | Hazem Lababidi | TC - 289 to TC - 290 | Passed | ____
Req - 26 / SRS - 3.2.4.4 | Admin defines languages | Product Owner | Admin > Qualifications > Languages | Scope - 3.2.4 | As an HR Admin, I want to list company languages with validation | Ahmed Abdallatif | TC - 291 to TC - 303 | Failed | Bug - 35 / Bug - 36 / Bug - 37
Req - 27 / SRS - 3.2.4.5 | Admin manages memberships | Product Owner | Admin > Qualifications > Membership | Scope - 3.2.4 | As an HR Admin, I want to track employee professional memberships | Majd Abu Hassanien | TC - 204 to TC - 310 | Failed | Bug - 38
Assigned To
Ahmed Abdallatif
Majd Abu Hassanien
Hazem Lababidi
Ehab Halabi
Hanna Farhoud
Current Staus
Passed
Failed